## A. Project Risk Matrix
Project Risk Matrix - [Project Name] |  |  |  |  | IMPACT | LIKELIHOOD
A Risk Matrix is a core tool to ensure PCM programs mitigate risk in order to do no harm. It does this by anticipating and acting on (1) risks affecting the achievement of outcomes for our service users and (2) risks affecting the wellbeing of clients and partners, including potential unintended harm resulting from PCM intervention. |  |  |  | High | Significant impact; success not achievable or unlikely | Very high probability to occur
|  |  |  | Medium | Some measurable impact to budget, workplan, quality or success | Likely to occur
|  |  |  | Low | Minimal impact to budget, workplan, quality or success | Some probability to occur
# | Risk | Impact on Women and Girls | Impact on Men and Boys | Impact (High, Medium, Low) | Likelihood (High, Medium, Low) | Mitigation Strategy | Resources Required (Costs)
Client Safety – Risks related to PCM clients' safety and how PCM programming may affect safety in the home/family/community
| Example: Women at risk of domestic /gender-based violence being the direct beneficiary of cash | Women are not able to use the benefits of the cash as it is taken by the husband. Psychological trauma for women and children from abuse | Increased family friction with husbands | Medium | Low | - Engage and sensitize husbands in the process of the cash transfers - Protection monitoring mechanism | No additional resources
Client Access – Risks related to the ability to participate and benefit from the program services (gender inequity, marginalization, rights, mobility, restrictions of movement, intellectual ability, etc.)
| Example: Due to IDPs living in hard-to-reach locations, accessibility to services becomes a challenge, particularly for PWDs, elderlies, children and women | Women and adolescent girls unable to access the project and livelihood services |  | Low | Low | Make adjustments in the project design to offer a mix of mobile and static services to cover the large population in targeted districts | Allocation of new budget lines that support mobile service delivery. Purchase of vehicle to reach remote locations
Stakeholders & Politics – Risks related to influential actors, government and politics (political events, power dynamics, policy shifts, etc.)
| Example: National government in KP region wants development activities. It is against programming that supports IDPs and puts in place barriers to PCM delivering services. | Humanitarian protection for IDPs is restricted | Humanitarian protection for IDPs is restricted | Low | Medium | Advocacy with the relevant stakeholders for the unmet humanitarian needs of the IDPs | No additional resources
Transition – Risks related to successful transition/closeout of program
Reputation & Access – Risks related to safety, security, and approval for PCM's staff and partners
| Example: Access to FATA region not possible due to delays from national government in issuing permissions |  |  | Low | High | Shift programming from FATA region to KP region - provide services to most vulnerable of those accessible, while keeping a certain percentage of emerging needs budget for FATA district | Realign existing resources
Conflict – Risks related to tension in the community and how PCM programming may affect tension in the community
| Example: Tension among the community members due to programming primarily focused on IDPs | Social exclusion | -Less opportunities to access economic opportunities -Social exclusion | Medium | Low | - Project will offer services to all vulnerable population affected by the displacement (including both host community and IDPs) - Community protection committees having representation from both IDPs and hosts will be involved extensively in beneficiaries selection process | No additional resources, change in targeting strategy
Economy – Risks related to the economy (e.g. hyper inflation, market failure, etc.) and barriers to economic participation
Environment – Risks related to the natural environment and manmade risks (e.g. drought, flooding, pollution, landmines, etc.)

## B. Risk Action Plan
Project Risk Action Plan - [Project Name]
A Risk Action Plan ensures that the strategies identified in the Risk Matrix are acted upon by identifying specific action steps, clear roles and responsibilities for the action steps, and a timeline for completion.
# | Risk | Mitigation Strategy | Resources Required (Cost) | Action Step | Focal Point | Timeline
PCM Reputation & Access
| Example: Access to FATA region not possible due to delays from national government in issuing permissions | Shift programming from FATA region to KP region - provide services to most vulnerable of those accessible, while keeping a certain percentage of emerging needs budget for FATA district | Realign existing resources | - conduct assessment in the new districts in KP region for expanding programs -revise project design/ budget as per needs | Team Leader | 2018-08-01
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
Conflict
| Example: Tension among the community members due to programming primarily focused on IDPs | - Project will offer services to all vulnerable population affected by the displacement (including both host community and IDPs) - Community protection committees having representation from both IDPs and hosts will be involved extensively in beneficiaries selection process | No additional resources, change in targeting strategy | - engagement of community committees (comprised of both IDPs and host community members) in the selection of vulnerable population and in delivery of services - organize social cohesion activities in the field | Project Manager | Ongoing
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
Economy
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
Environment
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
Client Safety
|  |  | No additional resources |  | Protection Officer | Ongoing
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
Client Access
| Example: Due to IDPs living in hard-to-reach locations, accessibility to services becomes a challenge, particularly for PWDs, elderlies, children and women | Make adjustments in the project design to offer a mix of mobile and static services to cover the large population in targeted districts | Allocation of new budget lines that support mobile service delivery. Purchase of vehicle to reach remote locations | - revise project delivery model and budget to incorporate mobile activities for the distant locations - discussed with and approved by donor - record and document the learning of this model and make improvements | Technical Coordinator | 2018-01-01
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
Stakeholders & Politics
| Example: National government in KP region wants development activities. It is against programming that supports IDPs and puts in place barriers to PCM delivering services. | Advocacy with the relevant stakeholders for the unmet humanitarian needs of the IDPs | No additional resources | Regular orientation of and coordination meetings with relevant authorities about project's area-based support and how it is improving the resilience of targeted communities | Project Manager / Team Leader | ongoing
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
Transition
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| Populated from Tab A. Risk Matrix | Populated from Tab A. Risk Matrix | Populated from Tab A. Risk Matrix

## Data Fields (hidden)
Data Fields
#REF! | #REF! | #REF!
Yes | External Sources (e.g. UN reports, WFP, Clusters, etc.) | Context Monitoring (External Risk)
No | IRC ERD Team | Do No Harm / Inclusivity (Internal Risk)
IRC Health Team
IRC VPRU (Protection Monitoring Team)
IRC Security Team
Project Monitoring Plan (including Client Feedback Plan)
GPC Protection Mainstreaming Resources